## Sheet1
Group 6 Drowsy Driving Detector Gantt Chart
| Weight | T1 W1 | T1 W2 | T1 W3 | T1 W4 | T1 W5 | T1 W6 | T1 W7 | T1 W8 | T1 W9 | T1 W10 | T1 W11 | Christmas Holiday | T2 W1 | T2 W2 | T2 W3 | T2 W4 | T2 W5 | T2 W6 | T2 W7 | T2 W8 | T2 W9 | T2 W10 | T2 W11 | Easter Holiday | T3 W8 | T3 W9
BB Sign-up
Proposals for 3 problems | 7%
Give Feasibility Study
Response
Product Design Specification | 3%
Think about Five Solutions
Meet with the supervisor: Stathaki T
Start to Write Preliminary Reprot
Finish and Submit Preliminary Report | 15%
Subgroups and Research
Individual Study
United Subgroups Meeting
Subgroups1 Designing Prototyping
Subgroups2 Designing Prototyping
Subgroups3 Designing Prototyping
Subgroups4 Designing Prototyping
Joining together all Parts
Tests and Improvements
Prepare for the Poster and Ptint | 30%
Prepare for the Demo and Presentation
Start to Write Final Reprot
Finish and Submit Final Report | 30%
Portfolio | 10%
Peer Assessment | 5%
Creater: | Sheng Yu
Last Update by: | Sheng Yu
Last Update Date: | 2018-11-25
Unmarked Step
Marked Step